TIKER

Engineering Spec

Priorities, Dependencies & Build Order

Reference companion to: TIKER-PRODUCT-VISION.docx

March 2026  |  v1.0  |  Confidential

# 1. Priority Framework

Every feature is assigned a priority level that determines build order. Higher priorities are built first; lower priorities are explicitly deferred until the preceding tier ships.

| Level | Meaning | Timeline | Gate |
| --- | --- | --- | --- |
| P0 | Ship immediately. Core value prop. Without this, the product pivot doesn’t land. | Weeks 1-2 | Must ship before any marketing or landing page changes. |
| P1 | Ship next. Completes the Tier 1 experience. Users expect these within days of P0. | Weeks 3-4 | Must ship before public launch or press. |
| P2 | Tier 2 intelligence. Makes the product sticky and differentiated. Build after launch. | Weeks 5-10 | Requires validated P0/P1 usage data. |
| P3 | Tier 3 autonomy. The full vision. Build when trust and retention are proven. | Weeks 11-20 | Requires proven retention (30d > 50%). |

# 2. Master Feature List

Every feature, ordered by priority. This is the single source of truth for what gets built and in what order.

## 2.1 P0: Ship Immediately (Weeks 1-2)

These features define the product pivot. Without them, Tiker is still a task manager.

| # | Feature | Priority | Effort | Depends On | Files / Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Briefing Engine API | P0 | 3 days | None | New /api/briefing/generate. Pulls calendar, tasks, agent activity. Claude Haiku synthesis. |
| 2 | Briefing Cron Job | P0 | 1 day | #1 | Vercel Cron at 6 AM. Per-user timezone. Stores result in new briefings table. |
| 3 | Briefings DB Table | P0 | 0.5 day | None | Migration: briefings (id, account_id, date, content JSONB, created_at). RLS. |
| 4 | Briefing Tab Redesign | P0 | 2 days | #1 | Rewrite DailyBriefing.tsx. Show generated briefing. Briefing + calendar hybrid layout. |
| 5 | Default View: Briefing | P0 | 0.5 day | #4 | Update ViewSwitcher default. Update /command to load briefing first. |
| 6 | Gmail Scan: Flights & Hotels | P0 | 2 days | None | Composio GMAIL_LIST_MESSAGES. AI classification for confirmations. Extract dates, conf #s. |
| 7 | Auto-Create Calendar Events | P0 | 1 day | #6 | From extracted flights/hotels. Composio GOOGLECALENDAR_EVENTS_CREATE. |
| 8 | Calendar Conflict Detection | P0 | 1 day | #1 | Compare calendar events for overlaps. Surface in briefing with recommendation. |

## 2.2 P1: Ship Next (Weeks 3-4)

Completes the Tier 1 experience. The product feels whole.

| # | Feature | Priority | Effort | Depends On | Files / Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Gmail Scan: Bills & Due Dates | P1 | 2 days | P0 #6 | Recurring sender + amount pattern matching. Store in extracted_items table. |
| 2 | Gmail Scan: Unresponded Invites | P1 | 1 day | P0 #6 | Flag calendar invites with no RSVP. Surface in briefing. |
| 3 | Meeting Prep: Attendee Lookup | P1 | 2 days | None | LinkedIn via Composio. Enrich attendees from calendar events. |
| 4 | Meeting Prep: Prior Context | P1 | 2 days | #3 | Search tasks/comments for attendee name or company. Summarize with AI. |
| 5 | Meeting Prep: Briefing Card | P1 | 1 day | #3, #4 | New component. Attendee bios, last meeting, open items, talking points. |
| 6 | Smart Reminders: Escalation | P1 | 2 days | None | If task not done: re-notify at +1d, +3d, +7d. Configurable. New reminders table. |
| 7 | Briefing Email Delivery | P1 | 1.5 days | P0 #1, #2 | HTML email template. Opt-in per user. Morning delivery via Nodemailer or Resend. |
| 8 | User Preferences: Briefing | P1 | 1 day | P0 #4 | Settings UI: delivery time, email opt-in, sections to include/exclude. |
| 9 | Landing Page Rewrite | P1 | 2 days | None | New hero, messaging, use cases. 'Your life, handled.' See vision doc Section 8. |
| 10 | Fix Broken Integrations | P1 | 1 day | None | X/Twitter connection. LinkedIn testing. Hide non-functional integrations. |

## 2.3 P2: Intelligence Layer (Weeks 5-10)

Makes the product sticky. Data-driven features that get better over time.

| # | Feature | Priority | Effort | Depends On | Files / Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Email Action Item Extraction | P2 | 3 days | P0 #6 | AI scans emails for implied commitments. 'You told Mike you'd send by Friday.' |
| 2 | Subscription & Trial Tracker | P2 | 2 days | P1 #1 | Detect recurring charges, trial signups from welcome emails. Alert before expiry. |
| 3 | Life Admin Research Agent | P2 | 5 days | None | Agent type: 'life_admin'. Web search + checklist generation. Passport, disputes, etc. |
| 4 | Contextual Smart Lists | P2 | 3 days | None | Shopping, errands, packing. Calendar-aware: 'guests Saturday' suggests grocery items. |
| 5 | Proactive Suggestions Engine | P2 | 5 days | P0 #1, P1 #1-4 | AI analyzes patterns across all data. 'You haven't seen a dentist in 14 months.' |
| 6 | Integration Passive Value | P2 | 5 days | P0/P1 | Each integration auto-surfaces insights. See vision doc Section 5 table. |
| 7 | Push Notifications (Web) | P2 | 2 days | P1 #6 | Service worker. Permission flow. Briefing + reminder delivery. |
| 8 | Mobile-First Briefing View | P2 | 3 days | P0 #4 | Responsive redesign. Swipeable cards. Touch-optimized actions. |

## 2.4 P3: Autonomy (Weeks 11-20)

The full vision. Tiker acts on your behalf with your approval.

| # | Feature | Priority | Effort | Depends On | Files / Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | AI-Initiated Booking | P3 | 10 days | P2 #3 | Flights, restaurants, appointments. Research + present options + book on approval. |
| 2 | Autonomous Task Completion | P3 | 8 days | P2 #3, #5 | Agent handles multi-step tasks end-to-end. Approval gates at key decisions. |
| 3 | Payment Integration (Plaid) | P3 | 10 days | P1 #1 | Financial awareness. Bill tracking, spending summaries. Requires Plaid partnership. |
| 4 | AI Phone Agent (ElevenLabs + Twilio) | P3 | 15 days | P2 #3 | Voice agent makes calls. Disputes, appointments, inquiries. Natural voice via ElevenLabs. |
| 5 | Proactive Schedule Optimization | P3 | 5 days | P0 #8, P2 #5 | 'You have 6h of meetings today, no focus time. Want me to reschedule the 3pm?' |
| 6 | Multi-Person Coordination | P3 | 8 days | P3 #1 | Family/team scheduling. 'Find a time that works for everyone for dinner.' |
| 7 | Voice Interface | P3 | 10 days | P3 #4 | 'Hey Tiker, what's my day look like?' Uses ElevenLabs for TTS. |
| 8 | Agent Marketplace | P3 | 15 days | P2 #3 | Third-party agents and integrations. Review, install, rate. |

# 3. Dependency Graph

Critical path items and what they unlock. Read top-to-bottom as build order.

| Feature | Blocked By | Unlocks | Status |
| --- | --- | --- | --- |
| Google Calendar Sync | None | Briefing Engine, Conflict Detection, Meeting Prep | Done |
| Composio Gmail Access | None | Email Scanning (all types) | Done |
| Briefings DB Table | None | Briefing Engine, Cron Job | Not Started |
| Briefing Engine API | Briefings DB Table | Cron Job, Briefing Tab, Email Delivery, Conflict Detection | Not Started |
| Gmail Scan: Flights | None | Auto-Create Events, Bill Scanning, Action Item Extraction | Not Started |
| Briefing Tab Redesign | Briefing Engine API | Default View Switch, User Preferences, Mobile View | Not Started |
| Default View: Briefing | Briefing Tab Redesign | Landing Page Rewrite (can show real product) | Not Started |
| Meeting Prep: Attendee | None | Prior Context, Briefing Card, Proactive Suggestions | Not Started |
| Smart Reminders | None | Push Notifications, Proactive Suggestions | Not Started |
| Life Admin Agent | None | AI Booking, Phone Agent, Autonomous Completion | Not Started |
| Proactive Suggestions | Briefing + Email + Meeting Prep | Schedule Optimization, Autonomous Tasks | Not Started |
| ElevenLabs + Twilio | Life Admin Agent | Voice Interface, Full Autonomy | Not Started |

# 4. Critical Path

The fastest route to a shippable product pivot. These items must be completed in order; everything else can be parallelized around them.

|  | Step | Est. | Day | Why Critical |
| --- | --- | --- | --- | --- |
| 1 | Briefings DB migration | 0.5d | Day 1 | Everything else writes to or reads from this table. |
| 2 | Briefing Engine API | 3d | Day 1-3 | The core product. Synthesizes all data sources into one view. |
| 3 | Gmail flight/hotel scan | 2d | Day 1-2 | Parallel with #2. First 'wow' moment: email becomes intelligence. |
| 4 | Auto-create calendar events | 1d | Day 3 | Depends on #3. Closes the loop: scan email, create event. |
| 5 | Briefing Tab Redesign | 2d | Day 4-5 | Depends on #2. Users see the new product for the first time. |
| 6 | Default to Briefing view | 0.5d | Day 5 | Depends on #5. The product pivot is now visible. |
| 7 | Calendar conflict detection | 1d | Day 6 | Depends on #2. Briefing gets its first proactive insight. |
| 8 | Briefing Cron Job | 1d | Day 6 | Depends on #2. Briefings generate automatically every morning. |
| 9 | Bill scanning + meeting prep | 4d | Day 7-10 | P1 features. Briefing becomes genuinely useful daily. |
| 10 | Landing page rewrite | 2d | Day 11-12 | Can now screenshot real product. New messaging lands. |

Total critical path: ~12 working days to a fully repositioned product. Non-critical P1 items (smart reminders, broken integrations, user preferences) can be done in parallel or immediately after.

# 5. Database Changes Required

### New Tables

| Table | Columns | Priority |
| --- | --- | --- |
| briefings | id UUID PK, account_id FK, date DATE, content JSONB, sections JSONB, created_at TIMESTAMP | P0 |
| extracted_items | id UUID PK, account_id FK, source (email/calendar), source_id TEXT, type (flight/bill/invite/action_item), data JSONB, processed BOOL, created_at | P0 |
| meeting_preps | id UUID PK, account_id FK, event_id TEXT, attendees JSONB, context JSONB, generated_at TIMESTAMP | P1 |
| reminders | id UUID PK, account_id FK, task_id FK (nullable), message TEXT, next_fire TIMESTAMP, escalation_level INT, config JSONB | P1 |
| user_preferences | id UUID PK, account_id FK UNIQUE, briefing_time TEXT, briefing_email BOOL, briefing_sections JSONB, reminder_config JSONB | P1 |

All tables include RLS policies scoped to account_id. All text fields with user content use AES-256-GCM encryption, consistent with existing pattern.

# 6. New API Routes

| Method | Route | Purpose | Priority |
| --- | --- | --- | --- |
| GET | /api/briefing/generate | Generate today’s briefing for authenticated user | P0 |
| GET | /api/briefing/latest | Fetch most recent briefing from DB | P0 |
| POST | /api/briefing/cron | Cron endpoint: generate for all users | P0 |
| GET | /api/email/scan | Scan Gmail for extractable items | P0 |
| POST | /api/email/extract | Process and store extracted items | P0 |
| GET | /api/meeting-prep/[eventId] | Generate prep for a calendar event | P1 |
| GET | /api/reminders | List active reminders for user | P1 |
| POST | /api/reminders | Create or update a reminder | P1 |
| POST | /api/reminders/check | Cron: fire due reminders, escalate | P1 |
| GET/PUT | /api/preferences | Read/update user preferences | P1 |
| POST | /api/suggestions/generate | Generate proactive suggestions | P2 |
| POST | /api/life-admin/research | Research agent for life admin tasks | P2 |

# 7. Component Changes

### Modified Components

| Component | Change | Priority |
| --- | --- | --- |
| DailyBriefing.tsx | Major rewrite. Fetch generated briefing from API. Briefing+calendar hybrid layout. Meeting prep cards. | P0 |
| ViewSwitcher.tsx | Change default view to 'briefing'. Update view order. | P0 |
| /command/page.tsx | Load briefing data. Pass generated briefing to DailyBriefing. | P0 |
| CalendarView.tsx | Add extracted items (flights, bills) as visual markers on calendar days. | P1 |
| TaskDetailModal.tsx | Add 'reminder' config section. Show linked extracted items. | P1 |
| /settings/connections | Show per-integration value prop. Hide broken integrations. | P1 |
| page.tsx (landing) | Full rewrite. New hero, messaging, use cases, pricing frame. | P1 |

### New Components

| Component | Purpose | Priority |
| --- | --- | --- |
| MeetingPrepCard.tsx | Attendee bios, prior context, talking points. Used in briefing and calendar. | P1 |
| BriefingSection.tsx | Reusable section wrapper for briefing (collapsible, with icon + count). | P0 |
| ExtractedItemBadge.tsx | Visual badge for flight, bill, invite, action item in lists and calendar. | P0 |
| ReminderConfig.tsx | Reminder settings: frequency, escalation, message. Used in task modal. | P1 |
| BriefingEmail.tsx | React Email template for daily briefing email delivery. | P1 |
| SmartListView.tsx | Shopping, errands, packing lists with calendar context. | P2 |
| SuggestionCard.tsx | Proactive suggestion with approve/dismiss/snooze actions. | P2 |

# 8. Composio Tool Slugs Needed

Based on the GOOGLECALENDAR_EVENTS_LIST discovery, we need to verify these slugs before building. Each should be tested with ?debug=1 pattern.

| Service | Expected Slug | Purpose | Verified? |
| --- | --- | --- | --- |
| Calendar | GOOGLECALENDAR_EVENTS_LIST | Fetch events for briefing | Yes |
| Calendar | GOOGLECALENDAR_EVENTS_CREATE | Create events from email extractions | No |
| Gmail | GMAIL_LIST_MESSAGES | Scan inbox for extractable items | No |
| Gmail | GMAIL_GET_MESSAGE | Read full email content for extraction | No |
| Gmail | GMAIL_SEND_EMAIL | Send briefing email, drafted replies | No |
| LinkedIn | LINKEDIN_GET_PROFILE | Attendee lookup for meeting prep | No |
| Slack | SLACK_LIST_MESSAGES | Monitor channels for mentions | No |
| GitHub | GITHUB_LIST_NOTIFICATIONS | Track PR reviews, CI failures | No |

Lesson learned: Composio slugs follow TOOLKIT_RESOURCE_ACTION pattern (not TOOLKIT_ACTION_RESOURCE). Always try multiple variants with fallback array pattern established in calendar/route.ts.

# 9. Sprint Plan: Week 1

Day-by-day plan for the first week. Goal: a working briefing with email intelligence by Friday.

| Day | Build | Deliverable | Test |
| --- | --- | --- | --- |
| Mon | Briefings DB migration. Briefing Engine API (/api/briefing/generate). Gmail scan API skeleton. | API returns JSON briefing with calendar + tasks | curl /api/briefing/generate with auth cookie |
| Tue | Gmail scan: flight/hotel extraction. Wire email data into briefing engine. | Briefing includes email intelligence section | Send test flight confirmation, verify extraction |
| Wed | Auto-create calendar events from extractions. Calendar conflict detection. | Extracted flights appear on calendar. Conflicts flagged in briefing. | Book overlapping events, check detection |
| Thu | Briefing Tab Redesign. New DailyBriefing.tsx with generated briefing display. | Briefing tab shows real synthesized data | Visual review in browser, dark mode test |
| Fri | Default view switch. Briefing cron job. Polish and deploy. | Full P0 feature set live on testcloud | Morning cron fires, briefing visible on load |

# 10. Risks & Mitigations

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Composio slug discovery | Blocks email/calendar features | Medium | Build debug/fallback pattern from calendar fix. Test all slugs Day 1. |
| Gmail rate limits | Scan too many emails, hit quota | Medium | Batch scan (last 24h only). Cache results. Incremental processing. |
| AI synthesis cost | Daily briefing for N users = N Haiku calls/day | Low | Haiku is cheap (~$0.001/briefing). At 1000 users = $1/day. |
| Email extraction accuracy | False positives in flight/bill detection | Medium | Conservative classification. User can dismiss/correct. Feedback loop. |
| Scope creep into P2/P3 | Delays P0/P1 ship date | High | This doc exists to prevent it. Refer to priority framework. |
| Landing page pivot confusion | Existing users confused by new messaging | Low | Keep current features working. New messaging is additive, not replacing. |

# 11. Future Ideas (Unscoped)

Not prioritized, not specced. Captured here so they don’t get lost. Each represents a potential product expansion that reinforces the core thesis: "we get shit done for you."

### Browser Extension

A Chrome/Firefox extension that observes browsing activity and bridges it to Tiker. The extension sees what you’re actually doing in real time, which is a data layer that email and calendar can’t provide.

- Activity monitoring: Detects when you’re browsing flights, comparing products, reading articles, filling out forms. Tiker learns intent without you having to tell it.

- One-click capture: "Add to Tiker" button on any page. Browsing flights to London? Click once, Tiker creates a task with the flight details, dates, and price range pre-filled.

- Purchase tracking: Detects order confirmations, tracks shipping, sets return deadline reminders. "Your Amazon return window for the headphones closes in 3 days."

- Offer to finish: If you’re halfway through a form, comparing 6 tabs of hotels, or abandoned a checkout, Tiker can offer to take over: research the best option, complete the booking, handle the paperwork.

- Contextual suggestions: Browsing a restaurant? "Want me to make a reservation for Saturday?" Reading an article about tax deductions? "Want me to create a checklist for your tax prep?"

The extension turns Tiker from something you check in the morning into something that’s always with you, always watching for opportunities to help.

### Mobile App (Native)

A native iOS/Android app that goes beyond responsive web. The mobile app is where Tiker lives in your pocket.

- Morning briefing as push notification: Rich notification with your day’s highlights. Expandable. Actionable (approve, snooze, delegate).

- Quick capture via voice: "Hey Tiker, remind me to call the dentist" from your lock screen. Whisper API or native speech-to-text.

- Location-aware reminders: "Remind me to return the Amazon package when I’m near a UPS store." Geofencing + task context.

- Widgets: iOS widget showing today’s top 3 items. Glanceable. No app open required.

- Offline task capture: Create tasks and reminders without connectivity. Sync when back online.

### The Ecosystem Vision

Browser extension + mobile app + web dashboard + email intelligence + calendar sync + voice agent. Every surface of your digital life feeds into one system that understands what you need and acts on it. The tagline for the ecosystem: "We get shit done for you."

End of Spec